Project Name	: Explorer Interface For SA EO Datasets
Start Date	: 09 December 2011
End Dtae	: 02 March 2012
Project Manager	: Mr Derek Hohls
Project Sponsor	: Dr Anwar Vahed
Project Team	: Lestinah Mthombeni
: Nkululeko Qwabe

Task Progress Report

This is a task report on the project as stated above (heading). This report will serve as a measure of our progress against the plan that we have set out ourselves during the inception of this project.

Task No.	Task	Time Estimate	Status	Actual Time
1.	Search and find Earth Observation datasets / Ask colleagues on EO reasearch group for known datasets / Search online	3 days	Complete	3 days

After an e-mail we got from our our project manager on 12/14/2011 9:38 AM (see appendix A), we had to extend our task number 1 to also defining the metadata we will provide to user through this application. We also also brainstormed some ideas for the categories and sub-categories we will use for the information coming from the portals.

We have taken time to look at a few Earth Observation portals (see Appendix B)to research what is included on the metadata and what is common across platforms so we can define what we can include in our metadata. We also have looked-up and read on metadata standards.

Outcomes of task

We have realised that the data that we anticipate a user would want to see about the dataset is descriptive, rights and ownership, and distribution data/metadata. This includes the following:
- Tittle	: Name of dataset
- Description	: Short description of dataset
- Creation Date	: Date that the dataset was last modified
- Application	: Possible applications of dataset
- Custodian	: The person/organisation maintaining the dataset
- Temporal Coverage	: The duration of data collection
- Keywords	: Set of words used to describe the dataset
- Spatial Coverage	: The area the dataset provides data for
- Data Format	: The format of the dataset
- Online Resource URL	: Online address of dataset
- Licence	: The licence that governs the dataset

For the categories and sub-categories, we will have the nine societal benefit areas at the first level and have locations for the second level and datasets for each location at the third level. This will be set as in the following sample schema:
- Disasters
  - South African Datasets
    - Dataset
    - Dataset
  - Other Countries
    - Dataset
    - ...
- Health
  - ...
- Energy
  - ...
- Climate
  - ...
- Water
  - ...
- Weather
  - ...
- Ecosystems
  - ...
- Agriculture
  - ...
- Biodiversity
  - …

As for the “cherry on top”, we are still working on how we can get the meta-data live from the portals.

Appendix A

The e-mail from	: Derek Hohls
Date	: 12/14/2011 9:38 AM
Tittle	: On-going work

Hi

Now that the plan is drawn-up, I am expecting that over the Tues.Wed.Thur period that you locate a few EO data portals and, based on those, define what type of meta-data you will provide in the module you are going to create. (Note that the meta data should be applicable across any and all such portals; even though not every single one may have all the data you want. Also brainstorm some ideas around what sub-categories (if any) you will use for the information coming from those portals. A "cherry on top" would be to identify how you are going to get the meta-data "live" from the portal.

This by lunch-time on next Monday.

Thanks
Derek

PS In addition, please start running tests on the VisTrails workflows in the Demo_Workflows folder - start with the oldest and create a list of ones NOT working.

PPS Do you have access to the DST_GEOSS svn site?

Appendix B

A list of Earth Observation portals visited:

- http://saeos.qsens.net/spatial_search?saved=true&anytext=SOS&resulttype=html
  - South African Earth Observation System Portal
- http://geoportal.csir.co.za/GetRecords?anytext=WMS
  - The GetRecords results of a CoGIS WMS
- http://geoportal.csir.co.za/GetRecords?anytext=SOS
  - The GetRecords results of a CoGIS SOS
- http://www.eoportal.org/
  - Earth Observation Portal
- https://eoportal.eumetsat.int/userMgmt/login.faces
  - EUMETSAT EO portal
- http://www.esa.int/esaEO/
  - European Space Agency portal
- http://www.earthobservations.org/pr_popr.shtml
  - Group on Earth Observation portal
- http://www.geowebportal.org/web/guest/home
  - Group on Earth Observation portal
- http://www.wamis.co.za/
  - WAMIS portal
- http://oceanographicdata.org/REASoN_DataPortalAccess.html
- http://earthdata.nasa.gov/
- http://cgsm.ca/data.html
- http://www.geoportal.org/